# Joova Team Responsibilities

Sep 27, 2026

Two teams run the Joova Band launch: Operations (Suman, Prabin, Nabin) gets the product from the factory to the customer, and Technology and Marketing (Satya, Puzan) gets customers to buy it and keeps the app and website running.

## Operations: Suman, Prabin, Nabin

Operations owns everything physical: the factory, the stock, and every package until it reaches the customer. The split below is a suggestion so each area has one clear owner; change it to fit each person’s strengths.

| Person | Main area | Responsibilities |
| --- | --- | --- |
| Suman | Factory and ordering | Factory contract and proforma invoice; deposit and balance payments; golden sample approval; production follow-up with the China partner; final inspection; reorders |
| Prabin | Shipping and compliance | Air freight booking; customs broker and customs bond; tariff code; FCC and ISED paperwork, UN38.3 and battery documents; barcodes and box labels (English and French); Amazon shipments to its warehouses |
| Nabin | Warehouse and customer orders | The 150 units kept in the US; website and TikTok Shop order packing and shipping; returns, size and color swaps, warranty replacements; stock counts and spare units; low-stock alerts to Suman |

Team goals: stock never runs out (more than 45 days left), orders ship within 1 business day, return rate below 8%.

## Technology and marketing: Satya, Puzan

This team owns everything digital: the app, the stores online, and how people hear about Joova. As above, the split is a suggestion.

| Person | Main area | Responsibilities |
| --- | --- | --- |
| Satya | App, website and stores | Apple and Google developer accounts; publishing the Joova app with the factory; app updates and the developer kit in the next phase; Shopify website, checkout, order tracking page, warranty and privacy pages; Amazon listing, photos and A+ content; TikTok Shop setup; support tools (help desk, live chat) |
| Puzan | Marketing and social media | Claim @joova on every platform; daily posts and short videos; the 50-creator program; Amazon, TikTok and Meta ads; waitlist and welcome emails; Amazon Vine; replying to reviews; press outreach |

Team goals: app rated 4.3 stars or higher, Amazon conversion above 10%, ad cost below 30% of ad sales, 2,000 waitlist emails before launch.

## Shared items and working together

A few jobs belong to neither team yet. Give each one owner so nothing falls through.

| Item | Suggested owner | Why |
| --- | --- | --- |
| LLC, EIN, business bank account, budget and payments approval | Founders | Company and money decisions |
| JOOVA trademark and contract review with lawyers | Founders | Legal commitments |
| D-U-N-S number | Founders, handed to Satya | Needed for the Apple developer account |
| Customer support inbox (first reply to every question) | Nabin for orders and returns, Satya for app and tech questions | Each question goes to the person who can fix it |
| Product photos and video | Puzan, with samples from Suman | Marketing needs the golden samples |

### How the teams work together

- Weekly 30-minute meeting (Monday): stock left, sales, reviews, ad results, the next week’s deadlines.

- Handoffs to watch: Suman tells Puzan the arrival date so ads start on time; Nabin shares return reasons with Satya and Puzan so the listing and app can be fixed; Puzan warns Suman before big promotions so stock is ready.

- One shared tracker (a Google Sheet is enough) with each task, its owner and its due date.